## Sheet1
Sep-10-2009
2-Gates Fish Protection Demonstration Project Draft Environmental Assessment
Bureau of Reclamation Comment Matrix
Section No. | Section | Target Release Date | Date Received | Date comments provided | Notes
1 | Introduction | 2009-08-28 | 8/28/2009 & 8/31/09 & 9/1/09 | 2009-09-03
2 | Project Description | 2009-08-31 | 2009-08-31 | 2009-09-03
3.1 | Aesthetics | 2009-09-01 | 2009-09-01 | 2009-09-03
3.2 | Agricultural Resources | 2009-09-01 | 2009-09-01 | 2009-09-03
3.3 | Air Quality | 2009-09-01 | 2009-09-01 | 2009-09-11
3.4 | Aquatic Bio Resources | 2009-09-01 | 2009-09-09 | 2009-09-11
3.5 | Terr Bio Resources | 2009-09-01 | 2009-09-01 | 2009-09-11
3.6 | Cultural Resources | 2009-09-01 | 2009-09-03 | Comments to be provided week of 9/14/09 | Section incomplete due to lack of access to Mandeville Island.
3.7 | Geology | 2009-09-01 | 2009-09-01 | 2009-09-03
3.8 | Hazards/Haz Materials | 2009-09-01 | 2009-09-02 | Comments to be provided 9/14/09
3.9 | Hydrology | 2009-09-01 | Draft version provided 9/2/2009. Final Version not received. | Comments to be provided when final version received. | Draft version provided was not complete. Accompanying email stated it was rough and may need a bit more information, and was provided to look at new level-of-detail.
3.1 | Noise | 2009-09-01 | 2009-09-02 | 2009-09-11
3.11 | Public Services | 2009-09-01 | 9/2/2009 | Comments to be provided 9/14/09
3.12 | Recreation | 2009-09-01 | 2009-09-03 | 2009-09-10
3.13 | Socioecon | 2009-09-01 | 9/2/2009 | 2009-09-11
3.14 | Transportation | 2009-09-01 | 9/2/2009 | Comments to be provided 9/14/09 | Boating impacts need to be reviewed by Scott Springer.
3.15 | Utilities | 2009-09-01 | 2009-09-02 | 2009-09-11
3.16 | Climate Change | 2009-09-01 | 2009-09-02 | 2009-09-11
4 | Cumulative Effects |  | 2009-09-02 | Comments to be provided 9/14/09
5 | Consultation/Coordination | 2009-08-28 | 8/28/2009 & 8/31/2009 | 2009-09-03
6 | References |  |  |  | Section not provided by contractor to Reclamation.
7 | List of Preparers |  |  |  | Section not provided by contractor to Reclamation.
| Appendices |  |  |  | Not provided by contractor to Reclamation.
| FONSI |  |  |  | Not provided by contractor to Reclamation.